**Log frame for the** Health **component**

|  | **Summary** | **Indicators** | **Sources of verification** | **Assumptions** |
| --- | --- | --- | --- | --- |
| **Goal** | People with disabilities achieve their highest attainable standard of health. | Mortality and morbidity rates for people with disabilities decrease by X%. | Local health centre statistics | Local government health-care services are available. |
| **Purpose** | People with disabilities are able to access the same health facilities and services as other members of the community. | 1. The number of people with disabilities attending local health centres increases by X% by end of year X.  2. X% of people with disabilities indicates a high level of satisfaction with local health services. | Local health centre statistics, mid-programme and end-of-programme evaluations | Local government health-care services are available. |
| **Outcome** | 1. People with disabilities have improved knowledge about their health and are active participants in achieving good health.  2. The health sector has increased awareness about disability.  3. Physical barriers within health-care facilities are reduced. | 1.1. X% of disabled people are actively involved in local self-help groups by year X.  1.2. Number of people with secondary conditions has decreased by X% by year X.  2. % of health-care workers attending disability equity training sessions by year X.  3. % of local health-care facilities that are physically accessible by year X. | 1. Attendance records, observation, reports from people with disabilities and families.  2. Observation, reports from people with disabilities and families.  3. Health facility audits, observation, end-of-programme evaluation. | People with disabilities are not excluded from accessing health-care services.  Local government healthcare services have adequate capacity. |
| **Activities** | 1.1 Give information to people with disabilities about the location of health-care facilities and services.  1.2 Set up self-help groups which focus on specific health issues.  2.1 Train workers at local health-care facilities about disability (including people with disabilities as trainers).  3.1 Carry out audits of health facilities to identify barriers that prevent access (including people with disabilities as auditors).  3.2 Hold meetings with people with disabilities and local health authorities to provide recommendations about ways to remove physical barriers. | **Resources needed**  **Human resources;**   * 1 programme manager * 2 CBR workers * 1 CBR trainer   **Materials**   * Information materials * Teaching materials * Training premises * Audit tool * Transport | **Cost**  Here a costing is provided for all the resources that are needed. | People with disabilities use the information they are given to access services.  People with disabilities are motivated to join and lead self-help groups.  Health-care workers apply the training they have received.  Ministry of health allocates resources to carry out modifications to buildings and offices. |